## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vinesh | 2026-09-03 | LangGraph duplicate tool execution error | Sprint 1 | Vinesh | Logical | Switched to create_react_agent from LangGraph prebuilt. | 30/08/2026 | Closed | Resolved
2 | Vinesh | 2026-09-03 | SQLite thread lock error during memory save | Sprint 1 | Vinesh | Database | Added try/except blocks and ensured conn.close() is called on every transaction. | 30/08/2026 | Closed | Resolved
3 | Vinesh | 18/09/2026 | Streamlit UI showing "0 Tool Calls" even when tools are executed. | Sprint 2 | Vinesh | Logical | Updated investigation_agent.py to count m.type == "tool" from React agent messages and increment global_metrics. | 18/09/2026 | Closed | Resolved
4 | Vinesh | 18/09/2026 | Groq API throwing "Rate Limit Exceeded (429)" / "Request too large" errors. | Sprint 2 | Vinesh | Logical | Switched DEFAULT_MODEL to llama3-8b-8192 | 18/09/2026 | Closed | Resolved
5 | Vinesh | 18/09/2026 | manage_incident tool crashing when provided an invalid action type. | Sprint 2 | Vinesh | Logical | Added validation to return an "Invalid action" error string | 18/09/2026 | Closed | Resolved
6 | Vinesh | 27/09/2026 | FastAPI server crashing with 'Connection reset by peer' when running complex 4-agent workflows. | Sprint 3 | Vinesh | Logical | Refactored /workflow/run endpoint from async to standard def thread pool worker. | 27/09/2026 | Closed | Resolved
7 | Vinesh | 29/09/2026 | SQLite database is locked error caused by connection leaks during rapid tool execution. | Sprint 3 | Vinesh | Logical | Added explicit conn.close() calls inside all early return paths within SQLite-backed tools. | 29/09/2026 | Closed | Resolved
8 | Vinesh | 30/09/2026 | System hallucinates logic when users query about completely unmonitored IT services. | Sprint 3 | Vinesh | Logical | Added CRITICAL RULE to prompt and python parsing logic to auto-generate INC-XXXX.md tickets. | 30/09/2026 | Closed | Resolved
.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others